## Slide 1
PROJECT PITCH PRESENTATION | BUSI 1725 PROJECT STUDY
CareRoute AI Assistant
Business Proposal for HealthRoute Ltd
Scenario 3 – AI-Powered GP Appointment and Triage System
Team: InnovateCare | Group 5 – September 2025
Members: Wiam Bakhattouch (1101736) | Abdelmoumen Fettaka | Chan Set Naung (1147717) | Rasuljon Murodov (1140707)
Date: 31 May 2025
Module Tutors: Oxford International Pathway Centres
BUSI 1725 – Project Study | Assessment 2 – Project Pitch Presentation

## Slide 2
Table of Contents
Oxford International Pathway Centres – BUSI 1725 Project Study | September 2025
01
Introduction & Scenario Overview
02
Key Challenges & Proposed Solutions
03
Project Life Cycle
04
Task Allocation – Belbin's Team Roles
05
Project Deliverables & KPIs
06
Risk Management Strategy
07
Project Plan & Gantt Chart
08
Estimated Budget
09
Summary
10
References

## Slide 3
Introduction & Scenario Overview
CareRoute AI Assistant – Business Proposal for HealthRoute Ltd
NHS England (2023); NHS Digital (2023) | Oxford International – BUSI 1725 Project Study | Sept 2025
Project Overview
CareRoute is an AI-powered triage and appointment booking system designed for independent GP practices across the UK. The Problem: The UK faces a severe GP access crisis, with over 300 million consultations annually and approximately 50% of patients waiting more than 2 weeks for an appointment (NHS England, 2023). Our Solution: CareRoute allows patients to describe their symptoms in any language and receive immediate guidance on the appropriate level of care, while automatically booking the correct appointment — reducing pressure on GP staff and improving patient outcomes. Client: HealthRoute Ltd – an independent GP network seeking digital transformation.
300M+
GP consultations
per year (NHS England, 2022)
50%
Patients wait >2 weeks
for appointment (NHS Digital, 2023)
75%
UK patients open to
digital health tools (Deloitte, 2022)
85–90%
AI triage accuracy
target (BMJ, 2020)

## Slide 4
Key Challenges & Proposed Solutions
NHS England (2023); BMJ (2020); Deloitte (2022) | Oxford International – BUSI 1725 Project Study | Sept 2025
CHALLENGE
Long GP Waiting Times
~50% of patients in England wait over 2 weeks for a GP appointment, causing delayed diagnosis and patient frustration (NHS England, 2023).
➜
SOLUTION
AI-powered instant triage directs patients to appropriate care level, cutting booking time by 30–40%.
CHALLENGE
Overloaded Administrative Staff
Receptionists handle high volumes of manual calls and bookings. Up to 30% of GP appointments could be automated (BMJ, 2020).
➜
SOLUTION
CareRoute automates appointment scheduling, reducing receptionist workload by 20–30%.
CHALLENGE
Inaccurate Self-Triage by Patients
Patients often book inappropriate appointment types (e.g., A&E for minor issues), wasting clinical resources and increasing costs.
➜
SOLUTION
Multilingual AI symptom assessment achieves 85–90% diagnostic accuracy (BMJ, 2020), routing patients correctly.
CHALLENGE
Low Digital Adoption in Healthcare
Many GP practices rely on outdated phone-based systems despite 75% of UK patients being open to digital health tools (Deloitte, 2022).
➜
SOLUTION
Simple, multilingual interface designed for all digital literacy levels; phone backup retained for non-digital users.

## Slide 5
Task Allocation – Belbin's Team Roles
Belbin (2010) – Roles matched to individual strengths and project needs
Belbin (2010) | Oxford International – BUSI 1725 Project Study | Sept 2025
AF
Abdelmoumen Fettaka
Resource Investigator
Strong focus on market research, competitor analysis, and identifying patient needs.
Healthcare market trends
Competitor analysis
Commercial opportunities
Patient pain points
RM
Rasuljon Murodov
Product Design Manager
Specialist in designing user experience and proposing innovative digital healthcare solutions.
User workflow design
AI interface concepts
User journey mapping
Interface prototypes
WB
Wiam Bakhattouch
Financial & Operations Manager
Responsible for budgeting, implementation strategy, and organising project structure.
Financial planning
Pricing model
Budget allocation
Project coordination
CS
Chan Set Naung
Project Coordinator & Ethics Manager
Focuses on ethics, risk analysis, project allocation, and final presentation review.
Risk analysis
Legal compliance
Quality assurance
Final report & slides
Belbin's Team Roles Theory: Roles allocated based on individual skills and strengths to maximise team performance (Belbin, 2010).

## Slide 6
Project Life Cycle
Initiation → Planning → Execution → Monitor → Closure | Kerzner (2017)
Kerzner (2017) | Oxford International – BUSI 1725 Project Study | Sept 2025
INITIATION
Week 1
Define healthcare problem & scope
Begin CareRoute research
Identify stakeholders (HealthRoute Ltd)
Secure initial project approval
▶
PLANNING
Weeks 1–2
Set project goals & KPIs
Develop detailed timeline & Gantt
Resource & budget allocation
Risk register creation
▶
EXECUTION
Weeks 3–5
Develop AI triage system
Build multilingual interface
Test booking algorithm (85–90% accuracy)
Conduct patient surveys & GP interviews
▶
MONITOR
Weeks 3–5
Track deadlines & task progress
Review KPI performance
Quality checks on deliverables
Team coordination meetings
▶
CLOSURE
Weeks 5–6
Final report & presentation
Evaluate project outcomes
Stakeholder feedback
Full pilot programme handover

## Slide 7
Project Deliverables & KPIs
Measurable outcomes linked to CareRoute's objectives
NHS England (2022); NHS Digital (2023); BMJ (2020); Deloitte (2022) | Oxford International – BUSI 1725 Project Study | Sept 2025
Key Deliverables
Deliverable | Type
AI Triage Algorithm (85–90% accuracy) | Tangible – Software
Multilingual Patient Interface (web/app) | Tangible – Product
GP Clinic Pilot Programme (2–3 clinics) | Tangible – Service
Patient Satisfaction Survey System | Tangible – Tool
Booking Time Reduction (30–40%) | Intangible – Efficiency
Workload Reduction Report (20–30%) | Intangible – Report
KPI Targets
Chart: KPI Target Improvements (%)
| Booking Time Reduction | Patient Satisfaction | Adoption Rate | Triage Accuracy | Workload Reduction
Target (%) | 35 | 85 | 65 | 87.5 | 25
Sources: NHS England (2022); NHS Digital (2023); BMJ (2020); Deloitte (2022)

## Slide 8
Project Outcomes
Expected results and justification based on NHS evidence
NHS England (2022); NHS Digital (2023); BMJ (2020) | Oxford International – BUSI 1725 Project Study | Sept 2025
OUTCOME | DESCRIPTION | WHY IT MATTERS
Booking time ↓ 30–40% | AI triage enables faster scheduling, reducing patient waiting | ~50% of patients wait over 2 weeks for a GP appointment (NHS England, 2023)
Access to care ↑ 25–35% | Patients directed to appropriate care (urgent, routine, self-care) | Accurate triage improves safety and efficiency (BMJ, 2020)
Workload ↓ 20–30% | Automation reduces manual calls and bookings by reception staff | Up to 30% of GP appointments could be automated (BMJ, 2020)
Patient satisfaction 85%+ | Faster access and improved communication with healthcare providers | High satisfaction reflects improved healthcare experience (NHS England, 2022)
Adoption rate 60–70% | Majority of patients regularly use AI system for bookings within 1 year | Strong adoption reflects trust and platform effectiveness (NHS England, 2022)

## Slide 9
Risk Management Strategy
ICO (2023); BMJ (2020); NHS Digital (2023) | Oxford International – BUSI 1725 Project Study | Sept 2025
Risk Register
RISK | LIKELIHOOD | IMPACT | RESPONSIBLE
Data Security Breach | HIGH | HIGH | Chan
AI Inaccurate Triage | MEDIUM | HIGH | Rasuljon
System/Tech Failure | MEDIUM | HIGH | Rasuljon
Patient Trust/Adoption | HIGH | MEDIUM | Moumen
Digital Accessibility | MEDIUM | MEDIUM | Moumen
Legal/GDPR Non-compliance | LOW | HIGH | Chan
Budget Overrun | MEDIUM | MEDIUM | Wiam
Key Risk Distribution
Chart: 
| Patient Trust & Adoption | Data Security | AI Accuracy | Digital Access | Legal/Compliance | Budget Risk
Risk Share | 30 | 20 | 20 | 15 | 10 | 5
Key Mitigations
🔒 Data Security Apply GDPR procedures; encrypted cloud storage (ICO, 2023)
🤖 AI Accuracy GP review of AI recommendations; continuous system updates (BMJ, 2020)
📱 Accessibility Phone booking backup; simple multilingual interface design
💰 Budget Regular spending monitoring; contingency fund allocation (Wiam)

## Slide 10
Project Plan & Gantt Chart
6-week implementation timeline for CareRoute development
Kerzner (2017) | Oxford International – BUSI 1725 Project Study | Sept 2025
Project Milestones & Task Timeline
TASK / ACTIVITY | LEAD | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Market Research & NHS Analysis | Moumen | █ | █ |  |  |  | 
Project Planning & KPI Setting | All | █ | █ |  |  |  | 
AI Triage Algorithm Development | Rasuljon |  | █ | █ | █ |  | 
Multilingual Interface Design | Rasuljon |  |  | █ | █ |  | 
Financial Planning & Budget Model | Wiam |  | █ | █ | █ |  | 
Patient Surveys & GP Interviews | Moumen |  |  | █ | █ | █ | 
Risk Analysis & Ethics Review | Chan |  |  |  | █ | █ | 
GP Clinic Pilot (2–3 clinics) | All |  |  |  |  | █ | █
Final Report & Presentation Prep | All |  |  |  |  | █ | █
Presentation & Submission | All |  |  |  |  |  | █
Source: Project Life Cycle adapted from Kerzner, H. (2017). Project Management: A Systems Approach to Planning, Scheduling, and Controlling. 12th ed. New Jersey: Wiley.

## Slide 11
Estimated Budget Plan
Budget structured using the 7Ps Marketing Mix framework
BMJ (2020); Deloitte (2022) | Oxford International – BUSI 1725 Project Study | Sept 2025
Budget Breakdown by Stage
STAGE | WEEKS | BUDGET % | THEORY LINK
Research & Planning | 1–2 | 10% | Market Research
Development & Testing | 3–5 | 45% | Product
Marketing & Acquisition | 5–6 | 25% | Promotion
Implementation & Training | 6–7 | 20% | People & Process
TOTAL | 1–7 | 100% | 7Ps Framework
The budget reflects a structured approach aligned with the 7Ps Marketing Mix (BMJ, 2020;
Deloitte, 2022), with 45% development ensuring 85–90% AI accuracy, 25% marketing
targeting 60–70% adoption, and 20% implementation reducing workload by 20–30%.
Budget Allocation (%)
Chart: 
| Research & Planning (10%) | Development & Testing (45%) | Marketing & Acquisition (25%) | Implementation & Training (20%)
Budget | 10 | 45 | 25 | 20

## Slide 12
Research Process & Assumptions
Evidence-based approach to CareRoute development
ONS (2023); Deloitte (2022); NHS England (2023); BMJ (2020) | Oxford International – BUSI 1725 Project Study | Sept 2025
Research Process
1
Primary Data
100–150 patient surveys via Google Forms; 15–20 GP staff interviews
2
Data Channels
Instagram, LinkedIn, NHS forums, GP partnerships
3
Secondary Data
NHS reports, academic journals, healthcare studies
4
Data Analysis
Quantitative (KPIs/percentages) + Qualitative (user feedback)
Key Assumptions
✓
Patients have digital access
~92% of UK adults use the internet (ONS, 2023)
✓
GP clinics adopt digital tools
60%+ of GP appointments involve digital interaction (NHS England, 2023)
✓
AI delivers reliable triage
Digital triage can reach 85–90% accuracy (BMJ, 2020)
✓
Patients trust digital healthcare
75% of UK patients open to digital health services (Deloitte, 2022)

## Slide 13
Presentation Summary
🏥 The Problem
Over 300M GP consultations annually; 50% of patients wait >2 weeks for appointments (NHS England, 2023).
💡 Our Solution
CareRoute: AI-powered multilingual triage and appointment booking system for independent GP practices.
🎯 Key Outcomes
30–40% booking time reduction | 25–35% improved access | 85%+ patient satisfaction (BMJ, 2020).
📊 Market Opportunity
75% of UK patients open to digital health tools — ideal commercial timing (Deloitte, 2022).
💰 Budget Structure
45% development (AI accuracy) | 25% marketing (60–70% adoption) | 20% implementation.
✅ Risk Managed
GDPR compliance, GP review protocols, multilingual accessibility, and phone booking backup.
CareRoute is positioned as a fast, multilingual, accessible digital assistant for independent GP practices across the UK.

## Slide 14
Thank You
Questions & Discussion
Team InnovateCare | CareRoute AI Assistant Project
Wiam Bakhattouch | Abdelmoumen Fettaka | Chan Set Naung | Rasuljon Murodov
Oxford International Pathway Centres | BUSI 1725 Project Study | September 2025

## Slide 15
References
Harvard Referencing Style
Oxford International Pathway Centres – BUSI 1725 Project Study | September 2025
Babylon Health (2021) Digital healthcare and AI triage systems. Available at: https://www.babylonhealth.com (Accessed: 1 May 2026).
Belbin, R.M. (2010) Team Roles at Work. 2nd ed. Oxford: Butterworth-Heinemann.
BMA (2023) Safe working in general practice. British Medical Association. Available at: https://www.bma.org.uk (Accessed: 1 May 2026).
BMJ (2020) The potential of digital triage systems in primary care. British Medical Journal.
Deloitte (2022) Digital healthcare trends in the UK. Available at: https://www.deloitte.com (Accessed: 3 May 2026).
Information Commissioner's Office (ICO) (2023) Data security incidents in healthcare. Available at: https://ico.org.uk (Accessed: 2 May 2026).
Kerzner, H. (2017) Project Management: A Systems Approach to Planning, Scheduling, and Controlling. 12th ed. New Jersey: Wiley.
NHS Digital (2023) Appointments in General Practice. Available at: https://digital.nhs.uk (Accessed: 15 May 2026).
NHS England (2022) General practice statistics and consultation data. Available at: https://www.england.nhs.uk (Accessed: 7 May 2026).
NHS England (2023) Patient access and waiting times in primary care. Available at: https://www.england.nhs.uk (Accessed: 11 May 2026).
ONS (2023) Internet users in the UK. Office for National Statistics. Available at: https://www.ons.gov.uk (Accessed: 6 May 2026).
PwC (2021) UK public attitudes towards AI in healthcare. Available at: https://www.pwc.co.uk (Accessed: 13 May 2026).